## Sheet1
| Task | Responsible Unit | Status | Comment
1 | First team meeting "Who is Who" | all | done | attended: nrayanov, lgoychev, Vsabev, bubulina, TanqIovkova
2 | Create a GitHub repository | lgoychev | done | https://github.com/lgoychev/Team-Bration/
3 | Create a GitHub acconts | all | in progress | lgoychev: done; nrayanov: done
4 | Research for an existing application which can be use in the project | nrayanov, Vsabev
5 | Present to the team a general functionality of selected application and how it works | nrayanov, Vsabev
6 | Discuss and Modify the functionality of selected application to meet the project scopes. | all
7 | Research for best SRS templates or examples
8 | Research for best Use cases templates or examples
9 | Research for best Test scenarios templates or examples
10 | Research for best way to implement atomation tests with Selenium IDE
11 | Write a SRS document about selected application.
12 | Write a Use cases for application functionality
13 | Write a Test scenario fro functionality test.
14 | Create some automation tests using Selenium IDE
15 | Design and write a presentation of the project using slides, screens, mock-ups and etc.
16 | Preparing all documents and apllication for presentation.
17 | Preliminary presentation of the project
18 | Final Presentation of the project