## Sheet1
| Task | Responsible Unit | Status | Comment
1 | First team meeting "Who is Who" | all | done | attended: nrayanov, lgoychev, Vsabev, bubulina, TanqIovkova
2 | Create a GitHub repository | lgoychev | done | https://github.com/lgoychev/Team-Bration/
3 | Create a GitHub acconts | all | done | lgoychev: done; nrayanov: done
4 | Research for an existing application which can be use in the project | nrayanov, Vsabev | reject | reject this option we will create a own JAVA application
5 | Present to the team a general functionality of selected application and how it works | nrayanov, Vsabev | done | Codding the JAVA application to edit a XML file
6 | Discuss and Modify the functionality of selected application to meet the project scopes. | all | done | General functionality of app is to extraxt Contract number form xml document
7 | Research for best SRS templates or examples | lgoychev | done | added some interesting SRS documents
8 | Research for best Use cases templates or examples | lgoychev | done | added some interesting SRS documents
9 | Research for best Test scenarios templates or examples | lgoychev | done | added some interesting SRS documents
10 | Research for best way to implement atomation tests with Selenium IDE
11 | Write a SRS document about selected application. | lgoychev | in progress
12 | Write a Use cases for application functionality | bubulina, TanqIovkova | in progress
13 | Write a Testplan for functionality test. | Vsabev | in progress
14 | Create some automation tests using Selenium IDE
15 | Design and write a presentation of the project using slides, screens, mock-ups and etc. | lgoychev | in progress
16 | Check and discuss the code of application and all document for project | all | in progress
17 | Test and add bug for JCNEx | all | in progress
18 | Preparing all documents and apllication for presentation. |  | in progress
19 | Preliminary presentation of the project
20 | Final Presentation of the project